## Roadmap
Story ID | Epic | Epic Name | Sprint | Title | Description | Acceptance Criteria | Story Points | Assigned Role
REG-101 | E1 | Foundation & Configuration Framework | Sprint 1 | Project scaffolding & CI test harness | Stand up the regagg module inside the MCP server repo with an isolated pytest harness (in-memory DB + temp storage) runnable on every commit. | Module imports cleanly inside host server; pytest suite runs offline in <10s; CI-safe fixtures for DB and storage exist | 3 | Backend Engineer
REG-102 | E1 | Foundation & Configuration Framework | Sprint 1 | Regulator configuration schema & loader | Strict pydantic model for per-regulator YAML (connector type, sources, fetch method, rate limits, doc-type rules, backfill cutoff) with a fail-fast loader. | Invalid/unknown fields rejected at load; connector↔sources cross-validated; filename must match declared id; loader collects all errors for reporting | 5 | Backend Engineer
REG-103 | E1 | Foundation & Configuration Framework | Sprint 1 | Author 30 regulator configs + controlled taxonomy | One YAML per regulator across CA/US/EU-UK/APAC/INTL plus the controlled tag taxonomy and global settings files. | 30 configs parse and validate; taxonomy doc-types match code constants; every source starts verified:false | 3 | Backend Engineer
REG-104 | E1 | Foundation & Configuration Framework | Sprint 1 | Corpus database schema (9 tables) | SQLAlchemy models on the shared base for documents, versions, tags, edges, pending-edges, seen-URLs, runs, watermarks, regulators; matching hand-authored Postgres DDL. | Tables auto-create on both SQLite and Postgres; one-current-per-doc expressible; FKs and CHECK constraints enforced; DDL file shipped | 5 | Backend Engineer
REG-105 | E1 | Foundation & Configuration Framework | Sprint 1 | Corpus storage layout over storage abstraction | Normalized folder layout (current/archive/staging/_state per regulator) implemented over the host's local/S3 storage backend with artifact read/write helpers. | Layout identical for all regulators; copy/delete tree operations work on local and S3 semantics; meta.json round-trips | 3 | Full-stack Engineer
REG-106 | E1 | Foundation & Configuration Framework | Sprint 1 | Foundation verification gate | A no-network CI gate proving configs parse, taxonomy is in sync, and all corpus tables register/create. | Single command exits non-zero on any foundation defect; run in CI on every commit | 2 | Backend Engineer
REG-107 | E4 | Source Verification & Regulator Onboarding | Sprint 1 | Source verification harness | Automated verifier for every candidate source: reachability, content-type, parseability (incl. sitemap indexes), freshness; produces a per-regulator report. | Pass/warn/fail per source with reasons; sitemap-index recognized; report renders to markdown; harness is the only authority for verified:true | 5 | AI Engineer
REG-108 | E4 | Source Verification & Regulator Onboarding | Sprint 1 | Fixture recorder & per-regulator parse tests | Record each regulator's real source payloads once and run every connector against its recording in CI. | Fixtures recorded for all reachable regulators; parametrized test per regulator passes offline; recordings size-capped | 3 | AI Engineer
REG-109 | E1 | Foundation & Configuration Framework | Sprint 1 | BA: source map validation & regulator list sign-off | Validate the proposed 30-regulator list and candidate sources against business priorities; obtain sign-off. | Signed-off regulator list; discrepancies (dead feeds, blocked sites) logged as onboarding risks | 2 | Business Analyst
PM-S1 | E1 | Foundation & Configuration Framework | Sprint 1 | PM: sprint ceremonies, RAID log, stakeholder reporting | Recurring per-sprint PM allocation (~25%): planning, standups, review/retro, risk and dependency management. | Ceremonies held; RAID log current; sprint report issued | 0 | Project Manager
REG-201 | E2 | Versioning & Governed Storage | Sprint 2 | Atomic versioning protocol (override→archive) | Six-step crash-safe protocol: stage new version, record intent, copy current to timestamped archive, promote staging, finalize document row. | New doc creates v1; changed content archives prior version and increments version; unchanged content is a no-op; document identity stable across revisions | 8 | Backend Engineer
REG-202 | E2 | Versioning & Governed Storage | Sprint 2 | Crash-recovery reconciliation & invariant audit | Deterministic repair job that rolls half-applied updates forward, cleans orphan staging, and audits invariants (exactly one current per doc; archive append-only). | After any induced crash, reconcile restores a clean state with zero committed-data loss; violations are reported, never silently fixed twice | 5 | Backend Engineer
REG-203 | E2 | Versioning & Governed Storage | Sprint 2 | Chaos test suite for the versioning path | Automated tests that kill the pipeline after every protocol step and assert full recovery. | Crash injected at each of steps 1–5; invariants hold post-reconcile in all cases; reconcile idempotent | 3 | Backend Engineer
REG-204 | E3 | Collection Engine | Sprint 2 | Sitemap-diff connector | Detect new/changed URLs from sitemap.xml (incl. index recursion) plus listing pages, with lastmod fast-path skipping and include/exclude filters. | Sitemap+listing union deduplicated; known URLs with unchanged lastmod skipped; doc-type mapped from URL rules | 5 | AI Engineer
REG-205 | E3 | Collection Engine | Sprint 2 | RSS/Atom connector | Poll 1..n feeds per regulator with GUID→URL dedup, malformed-feed isolation, and backfill-cutoff filtering. | Duplicate GUIDs collapse; items older than cutoff ignored; one bad feed never aborts others | 3 | AI Engineer
REG-206 | E3 | Collection Engine | Sprint 2 | API connector & Federal Register adapter | Provider-adapter API connector; Federal Register: agency filters, explicit field selection, pagination to cutoff, sanctioned full-text URL, abstract capture. | Paginates until backfill cutoff; emits reference numbers for dedup; requests raw_text_url+abstract explicitly (not in default fields) | 5 | AI Engineer
REG-207 | E3 | Collection Engine | Sprint 2 | Fetch & normalization layer | Polite fetcher (UA, per-domain rate limit) converting HTML→markdown (boilerplate stripped) and PDF→markdown, detecting PDFs by magic bytes, flagging scanned files. | HTML preserves headings/tables/links; .pdf URLs serving HTML are treated as HTML (magic-byte truth); scanned PDFs flagged ocr:true; content sha256 computed | 5 | Full-stack Engineer
REG-208 | E2 | Versioning & Governed Storage | Sprint 2 | BA: provenance & audit acceptance walkthrough | Define and verify the governance chain a compliance reviewer needs: source URL, final URL, hash, timestamps, run attribution, raw original, version lineage. | Walkthrough from rendered doc back to original bytes and run manifest demonstrated; gaps (post-redirect URL) closed | 2 | Business Analyst
PM-S2 | E5 | Orchestration, Operations & Data Quality | Sprint 2 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager
REG-301 | E3 | Collection Engine | Sprint 3 | End-to-end ingestion pipeline | Wire detect→fetch→version→enrich→record per regulator: run manifests, seen-URL registry, per-URL error isolation, idempotent reruns. | One bad document never fails a run; rerun same day is a no-op for unchanged content; manifest lists every URL with outcome; run row persisted | 8 | Backend Engineer
REG-302 | E3 | Collection Engine | Sprint 3 | Policy-PDF harvesting | Extract same-domain PDF links from ingested HTML pages and ingest them as first-class policy documents (source_kind=policy_pdf), with per-page and per-run caps. | PDFs enter the same versioning path; source_kind recorded; caps prevent runaway; 3/page, 40/run defaults | 3 | AI Engineer
REG-303 | E3 | Collection Engine | Sprint 3 | Meta-source deduplication | When the meta-source (Federal Register) lists a document an agency feed already provided, keep the agency copy canonical and skip the duplicate by reference number. | Duplicate skipped and counted (deduped metric); no double-counting across fedreg/agency | 2 | AI Engineer
REG-304 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | Fleet orchestrator | Fan out one isolated run per active regulator; support rerun of all/subset/one for a chosen date; expose reconcile as an operation. | One regulator's hard failure never blocks others; rerun records operator identity; reruns are idempotent | 5 | Backend Engineer
REG-305 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | Run status semantics & live progress | Humane statuses (failed only when nothing landed or >20% errored) plus mid-run counter flushes so the UI can show live progress. | Partial-error runs show success + error count; counters update at least every 10 documents during a run | 3 | Backend Engineer
REG-306 | E4 | Source Verification & Regulator Onboarding | Sprint 3 | Pilot regulators end-to-end (OSFI, FRB, FedReg) | Prove all three connector types live against the pilot trio, including a forced content change correctly archiving v1. | All pilots ingest live; update archives prior version; fixtures recorded | 3 | AI Engineer
REG-307 | E4 | Source Verification & Regulator Onboarding | Sprint 3 | Onboarding wave 1 — fifteen fast regulators | Verify sources and run first live ingestion for the non-giant regulators across all regions. | Each has ≥1 verified source and a passing live run; failures triaged with per-URL evidence | 5 | AI Engineer
REG-308 | E3 | Collection Engine | Sprint 3 | Crawl hardening | Protect the fleet from pathological sources: sitemap byte cap, sitemap-index child cap, giants-last ordering with per-giant caps, tuned timeouts. | A monster sitemap cannot hang a run (logged truncation); giants capped per run; hardening covered by tests | 3 | Full-stack Engineer
REG-309 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | Bot-block guard & sanctioned fallbacks | Detect anti-scraping block pages and fall back to official API abstract, else an honest metadata stub — provenance labels content_source; never store block-page garbage; never evade. | Block page never stored as content; fallback chain full-text→abstract→stub; content_source recorded; zero recurring error storms | 2 | Full-stack Engineer
REG-310 | E7 | Analyst & Operator Dashboard | Sprint 3 | BA: dashboard information architecture & status vocabulary | Define analyst/operator journeys, coverage semantics (fresh/stale/attention), and plain-language status labels for the UI. | IA for 5 pages agreed; status color/meaning table documented | 2 | Business Analyst
PM-S3 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager
REG-401 | E7 | Analyst & Operator Dashboard | Sprint 4 | Dashboard data API | Read endpoints backing every page: coverage tree with roll-ups, corpus browse with facets, changes feed, run overview with daily delta, version diff, inventory, jailed file explorer. | All endpoints stateless and paginated where relevant; institution filters applied in SQL before LIMIT; fs endpoints jailed to corpus root | 5 | Backend Engineer
REG-402 | E7 | Analyst & Operator Dashboard | Sprint 4 | Coverage page | Region→institution expandable tree: web/PDF counts, new-in-window, last run, freshness pill, coverage-% vs source-advertised, per-row Run trigger. | Coverage % shown per institution; staleness flagged per config threshold; Run button triggers a real audited run | 5 | Full-stack Engineer
REG-403 | E7 | Analyst & Operator Dashboard | Sprint 4 | Corpus browser page | Dedicated deep-linkable page: continent/institution/file-type/doc-type/status/date/search filters with live facet counts, title+reference+excerpt rows, source links, Published+Added columns, pagination. | All filters server-side; facet counts reflect scope; row opens document drawer; 50/page with prev/next | 5 | Full-stack Engineer
REG-404 | E7 | Analyst & Operator Dashboard | Sprint 4 | Collection-runs page | Operations view: today's delta banner with pass-rate headline and failing-run digest, live active-run progress (5s polling), recent runs, daily delta history. | Pass-rate = fetched/(fetched+errors); live counters tick during runs; every run links to its manifest | 3 | Full-stack Engineer
REG-405 | E6 | Deterministic Enrichment & Knowledge Graph | Sprint 4 | Reference-number grammar & citation mining | Regex grammars for regulator identifiers (OSFI B/E-series, CAR/LAR chapters, SR letters, OCC bulletins, NI, APS, PS/CP/SS, RTS/ITS, BCBS…) extracting a document's own reference and its citations, with sentence-scoped supersede detection. | Own-reference extracted from titles; citations classified supersedes vs references without cross-sentence bleed; adding a grammar is a table entry | 5 | AI Engineer
REG-406 | E6 | Deterministic Enrichment & Knowledge Graph | Sprint 4 | Cross-reference knowledge graph | Resolve citations against the corpus into typed edges with confidence; supersedes edges flip target status; unresolved citations persist and retry nightly. | Edges deduplicated; supersedes updates target to superseded; pending edges resolve when the target arrives | 3 | AI Engineer
REG-407 | E6 | Deterministic Enrichment & Knowledge Graph | Sprint 4 | Expected-inventory reconciliation (completeness proof) | Per-regulator expected inventories (seeded: OSFI CAR/LAR/B/E series) reconciled against the corpus by reference then title; per-series present/missing report and API. | Answers 'do we hold every chapter?' with named gaps; OSFI reconciles 30/30 after gap-fill | 3 | AI Engineer
REG-408 | E4 | Source Verification & Regulator Onboarding | Sprint 4 | Onboarding wave 2 — giants & source remediation | Onboard the large/broken regulators: capped depth-slicing for giants; fix dead feeds (FDIC), connector switches (HKMA + 5 RSS-dead regs → listing/sitemap), sitemap-index support (CSA). | 29/30 regulators verified and collecting; each fix re-verified by the harness; AMF escalated (not evaded) | 3 | AI Engineer
REG-409 | E4 | Source Verification & Regulator Onboarding | Sprint 4 | Targeted gap-fill runs | URL-regex-scoped ingest (e.g. /en/guidance) so specific sections can be completed without full-site crawls; used to complete OSFI's guideline chapters. | Scoped run ingests only matching URLs; OSFI guidance section filled (363 docs) driving inventory to complete | 2 | Backend Engineer
REG-410 | E7 | Analyst & Operator Dashboard | Sprint 4 | BA: UAT round 1 (coverage/corpus/runs) | Structured UAT of the first three pages against analyst/operator journeys; log and triage defects. | UAT script executed; defects logged with severity; blocking defects fixed before sprint close | 2 | Business Analyst
PM-S4 | E5 | Orchestration, Operations & Data Quality | Sprint 4 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager
REG-501 | E7 | Analyst & Operator Dashboard | Sprint 5 | Changes / impact feed | Analyst delta feed: NEW/REVISED/SUPERSEDED/DEADLINE cards grouped by day, filtered by region, institution, file type, change-type chips, and explicit date range — all server-side. | Filters share coverage-tree dimensions; counts remain pre-kind-filter for tile toggles; feed matches DB deltas exactly | 3 | Full-stack Engineer
REG-502 | E7 | Analyst & Operator Dashboard | Sprint 5 | Version diff viewer | One-click unified diff between a document's current and previous archived version with added/removed counts, from the Changes feed and drawer. | Diff renders color-coded; single-version docs report 'no diff' cleanly | 2 | Full-stack Engineer
REG-503 | E7 | Analyst & Operator Dashboard | Sprint 5 | Rich document drawer | Document view with tabs: rendered markdown (self-contained md→html, no CDN), summary, provenance rail (all governance fields incl. final URL/fetch method/content source), raw text. | Headings/lists/tables/links render; provenance shows source URL clickable; raw preserved verbatim | 3 | Full-stack Engineer
REG-504 | E7 | Analyst & Operator Dashboard | Sprint 5 | Corpus file Explorer | Nested file-tree page mirroring disk (regulator→current¦archive→doc_type→year→doc→artifacts) with lazy loading; text files open in drawer, originals download; API jailed to corpus root. | Path traversal rejected (400); item counts and sizes shown; md renders rich | 3 | Full-stack Engineer
REG-505 | E5 | Orchestration, Operations & Data Quality | Sprint 5 | Manual interjection & upload lane | Human override: add/update a document by URL fetch, pasted corrected markdown, or uploaded PDF/HTML — via UI modal, API, and CLI — through the identical versioning/provenance path, tagged manual and audited. | Update archives prior version; operator identity recorded; run row visible; future crawls recognize the URL (no duplicates); 50MB upload cap | 5 | Backend Engineer
REG-506 | E8 | MCP Tool Surface & Security | Sprint 5 | Content-plane MCP tools | reg_search (filter-then-rank), reg_read (summary¦full¦meta¦historical version), reg_tags, reg_whats_new, reg_graph — stateless, registered via config-driven dynamic discovery. | All five discoverable and callable over MCP; filters applied before ranking; graph traversal cycle-safe depth≤3 | 5 | AI Engineer
REG-507 | E8 | MCP Tool Surface & Security | Sprint 5 | Index-plane MCP tools | reg_coverage, reg_browse (metadata-only), reg_changes, reg_diff, reg_inventory, reg_runs_status, reg_trigger_run (mutating, guarded) — the answers content-RAG cannot give. | All seven callable over MCP with the same filters as the UI; trigger refuses concurrent runs and records operator | 5 | AI Engineer
REG-508 | E8 | MCP Tool Surface & Security | Sprint 5 | MCP security & key lifecycle | Authentication required for tools/call (discovery stays open); per-key tool allowlists enforced at the transport; scoped agent key issued, rotated, and stored DB-only (never committed). | No-key and dead-key calls rejected; out-of-scope tool denied; in-scope tool works — four-way matrix verified; rotation procedure documented | 5 | Backend Engineer
REG-509 | E7 | Analyst & Operator Dashboard | Sprint 5 | BA: UAT round 2 (changes/diff/explorer/manual) | Structured UAT of the remaining pages and the manual lane. | UAT script executed; defects triaged; sign-off recorded | 2 | Business Analyst
PM-S5 | E5 | Orchestration, Operations & Data Quality | Sprint 5 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager
REG-601 | E9 | Agentic Integration | Sprint 6 | Markdown projection for the agent stack | Maintain the corpus in the agent tools' consumption layout — data/markdown/{web¦policy}/{regulator}/{doc_type}/{doc_id}.md with YAML frontmatter — via write-through on every ingest plus nightly resync self-heal. | Every current document has exactly one projection file; frontmatter carries citation context; resync idempotent; history stays in canonical store | 5 | Backend Engineer
REG-602 | E9 | Agentic Integration | Sprint 6 | Agent-platform MCP connectivity | Connect the existing agent stack to the MCP endpoint with the scoped key; verify end-to-end tool calls and denial of out-of-scope tools. | initialize/tools list/call verified from client side; connection details documented for the platform's custom-MCP dialog | 3 | AI Engineer
REG-603 | E9 | Agentic Integration | Sprint 6 | Chatbot enablement guide | Author the integration guide: connection block, agent prompt pattern (narrow→read cheap→relate→freshness), non-negotiable citation rule, worked examples, honest limitations, go-live eval checklist. | Guide sufficient for the chatbot team to integrate without our involvement | 2 | AI Engineer
REG-604 | E9 | Agentic Integration | Sprint 6 | Agent skills authoring | Author skill definitions on the agent platform mapping to the tools: Daily Regulatory Briefing (reg_changes), Impact Analysis (reg_diff+reg_graph), Completeness Audit (reg_coverage+reg_inventory). | Three skills live on the platform; each produces correct, cited output on test prompts | 3 | AI Engineer
REG-605 | E9 | Agentic Integration | Sprint 6 | Agent citation & accuracy evaluation | Run the 20-question eval across ≥8 regulators: every claim cited (regulator+reference+date+URL), superseded docs flagged with successor, out-of-corpus questions declined. | Eval sheet completed with pass/fail per question; failures fed back into prompt/tool fixes | 3 | AI Engineer
REG-606 | E5 | Orchestration, Operations & Data Quality | Sprint 6 | Daily delta poller & weekly deep run | Single scheduler entrypoint: fleet delta ingest (giants depth-sliced), pending-edge resolution, integrity reconcile, projection resync, one-line delta summary; weekly --deep raises caps. | One cron line each for daily/weekly; exit code signals invariant violations; every run visible in UI | 3 | Backend Engineer
REG-607 | E5 | Orchestration, Operations & Data Quality | Sprint 6 | Backup & restore | Nightly consistent SQLite snapshot + hardlink-incremental corpus backup with 7-day retention; restore verified. | Backup runs while server/crawls active; restore drill opens snapshot with full document count; retention enforced portably | 3 | Backend Engineer
REG-608 | E7 | Analyst & Operator Dashboard | Sprint 6 | UX polish round | Excerpt/description line + source links + Added date in corpus; PDF filename titles (incl. backfill); add-doc discoverability in top bar; rich-render defaults. | No raw URLs as titles; every row shows an honest excerpt where text exists; date column always populated | 3 | Full-stack Engineer
REG-609 | E10 | Future Enhancements (Backlog) | Sprint 6 | Successor knowledge base | Author the handover KB: start-here mental model, architecture/flows/schema, UI+tools reference, testing/ops runbook, known issues + war stories + roadmap. | A new engineer/AI agent can operate and extend the system from the KB alone | 3 | Full-stack Engineer
REG-610 | E9 | Agentic Integration | Sprint 6 | BA: final UAT & product-owner acceptance | End-to-end acceptance against the epic-level outcomes; PO sign-off for go-live. | Acceptance record signed; open items dispositioned to backlog | 2 | Business Analyst
PM-S6 | E5 | Orchestration, Operations & Data Quality | Sprint 6 | PM: go/no-go readiness review & handover | Deployment readiness review, handover of runbooks/KB, closure report. | Readiness review held; handover acknowledged | 0 | Project Manager
REG-701 | E10 | Future Enhancements (Backlog) | Backlog | Federal Register full text via govinfo.gov bulk data | Replace abstract/stub fallback with sanctioned full text from GPO govinfo bulk repository (separate host built for programmatic bulk use). | Full text for new FR docs; existing stubs self-heal to full text as revisions; no ToS risk | 5 | AI Engineer
REG-702 | E10 | Future Enhancements (Backlog) | Backlog | Simple-mode overview landing page | First-time-user landing: one plain-English headline, ≤4 tiles, one regulator×(web/PDF/today delta/health-dot) table; ops detail moves behind drill-ins; analyst vs operator modes. | New user answers 'what do we have / what changed today / is it healthy' in <10s without training | 5 | Full-stack Engineer
REG-703 | E10 | Future Enhancements (Backlog) | Backlog | Playwright fetch path for JS-heavy sites | Browser-rendered fetching for regulators whose listings require JavaScript (MAS, some NYDFS). | fetch:playwright configs ingest content where plain HTTP yields none | 5 | AI Engineer
REG-704 | E10 | Future Enhancements (Backlog) | Backlog | PostgreSQL migration | Flip db.type to Postgres using the shipped DDL; enable pg_trgm for title-similarity reference resolution. | All tests green on Postgres; no write-lock contention during concurrent crawl+agent load | 3 | Backend Engineer
REG-705 | E10 | Future Enhancements (Backlog) | Backlog | Expected inventories for EBA / FCA / APRA | Extend completeness proofs beyond OSFI using each regulator's official register/index. | Per-series present/missing for 3 more regulators; gaps drive targeted gap-fills | 3 | AI Engineer
REG-706 | E10 | Future Enhancements (Backlog) | Backlog | Weekly digest webhook | Teams/email digest generated from the changes feed (per-desk filters). | Scheduled digest delivered with citations; opt-in filters per audience | 3 | Backend Engineer
REG-707 | E10 | Future Enhancements (Backlog) | Backlog | AMF Québec access via official whitelisting | Engage AMF for institutional IP/UA whitelisting (site bot-blocks all automation); fallback: licensed feed. | AMF collecting via sanctioned access; zero evasion techniques used | 2 | Business Analyst
REG-708 | E10 | Future Enhancements (Backlog) | Backlog | Production hardening | Pre-exposure hardening: replace default admin credentials, TLS/reverse proxy, restricted bind, secrets management, key rotation SOP. | Security checklist passed before any non-localhost exposure | 5 | Backend Engineer
REG-709 | E10 | Future Enhancements (Backlog) | Backlog | OCR for scanned policy PDFs | Tesseract path for image-only PDFs (currently 6 docs, 97% extract fine without). | ocr:true docs gain searchable text; volume-triggered (revisit if scanned share grows) | 3 | AI Engineer
REG-710 | E10 | Future Enhancements (Backlog) | Backlog | LLM enrichment integration | Wire the owner's LLM gateway into the enrichment slot: real summaries (summary.md), taxonomy topic tags, doc-type reclassification, date/deadline extraction; golden-set eval gates. | Summaries replace excerpts; doc_type distribution reflects reality (not 90% announcement); deadline feed populated; eval ≥90% tagging accuracy | 8 | AI Engineer

## Epics
Epic | Name | Objective
E1 | Foundation & Configuration Framework | Config-driven skeleton: regulator-as-config YAML model, corpus database schema, storage layout, CI gates. Adding regulator #31 must never require code.
E2 | Versioning & Governed Storage | The trust core: one current copy per document, append-only archive, crash-safe atomic override protocol, full provenance (source URL, hash, run attribution, raw original).
E3 | Collection Engine | Three stateless connector engines (sitemap-diff / RSS / API), fetch & HTML/PDF→markdown normalization, PDF harvesting, dedup, pagination, crawl hardening.
E4 | Source Verification & Regulator Onboarding | No source is trusted until the verification harness passes it. Onboard all 30 regulators with recorded test fixtures and provable completeness (expected-inventory reconciliation).
E5 | Orchestration, Operations & Data Quality | Fleet fan-out with failure isolation, humane run statuses, live progress, daily delta pollers, manual interjection lane, backups, bot-block fallbacks.
E6 | Deterministic Enrichment & Knowledge Graph | No-LLM enrichment: reference-number grammars per regulator, citation mining into a supersedes/references graph, expected-inventory completeness checks.
E7 | Analyst & Operator Dashboard | Five-page UI: Coverage tree with coverage-%, Corpus browser, file Explorer, Changes/impact feed with diffs, Collection-runs monitor with live counters.
E8 | MCP Tool Surface & Security | Twelve stateless reg_* MCP tools (content + index planes), API-key lifecycle, authentication required for execution, per-key tool allowlists enforced.
E9 | Agentic Integration | Plug the corpus into the existing agent stack: markdown projection in the agent's consumption layout, scoped MCP connectivity, chatbot guide, agent skills, citation eval.
E10 | Future Enhancements (Backlog) | Post-MVP: govinfo full-text connector, simple-mode overview UX, Playwright fetch, Postgres, more inventories, digests, production hardening, LLM enrichment.

## Capacity
Role | Allocation | Days / Sprint | SP Capacity / Sprint | Sprints | Notes
Backend Engineer | 100% | 10 | 11 | 6 | Data layer, versioning, pipeline, ops
Full-stack Engineer | 100% | 10 | 11 | 6 | Dashboard UI, fetch layer, docs
AI Engineer | 100% | 10 | 11 | 6 | Connectors, enrichment, MCP tools, agentic
Business Analyst | 25% | 2.5 | 2 | 6 | Source sign-off, UX definitions, UAT
Project Manager | 25% | 2.5 | 0 | 6 | Ceremonies, RAID, reporting (non-pointed)
Planned SP by sprint (dev+BA):
Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Backlog
31 | 36 | 36 | 36 | 33 | 30 | 42