## Story Status
Story ID | Epic | Epic Name | Sprint | Title | Description | Acceptance Criteria | Story Points | Assigned Role | Status | Evidence / Notes
REG-101 | E1 | Foundation & Configuration Framework | Sprint 1 | Project scaffolding & CI test harness | Stand up the regagg module inside the MCP server repo with an isolated pytest harness (in-memory DB + temp storage) runnable on every commit. | Module imports cleanly inside host server; pytest suite runs offline in <10s; CI-safe fixtures for DB and storage exist | 3 | Backend Engineer | Done | tests/regagg/conftest.py; suite runs 92 tests in ~3s
REG-102 | E1 | Foundation & Configuration Framework | Sprint 1 | Regulator configuration schema & loader | Strict pydantic model for per-regulator YAML (connector type, sources, fetch method, rate limits, doc-type rules, backfill cutoff) with a fail-fast loader. | Invalid/unknown fields rejected at load; connector↔sources cross-validated; filename must match declared id; loader collects all errors for reporting | 5 | Backend Engineer | Done | config_models.py, config_loader.py; foundation gate 30/30
REG-103 | E1 | Foundation & Configuration Framework | Sprint 1 | Author 30 regulator configs + controlled taxonomy | One YAML per regulator across CA/US/EU-UK/APAC/INTL plus the controlled tag taxonomy and global settings files. | 30 configs parse and validate; taxonomy doc-types match code constants; every source starts verified:false | 3 | Backend Engineer | Done | config/regulators/*.yaml (30) + _taxonomy + _settings
REG-104 | E1 | Foundation & Configuration Framework | Sprint 1 | Corpus database schema (9 tables) | SQLAlchemy models on the shared base for documents, versions, tags, edges, pending-edges, seen-URLs, runs, watermarks, regulators; matching hand-authored Postgres DDL. | Tables auto-create on both SQLite and Postgres; one-current-per-doc expressible; FKs and CHECK constraints enforced; DDL file shipped | 5 | Backend Engineer | Done | regagg/models.py; db/scripts/postgresql/003_regagg_schema.sql
REG-105 | E1 | Foundation & Configuration Framework | Sprint 1 | Corpus storage layout over storage abstraction | Normalized folder layout (current/archive/staging/_state per regulator) implemented over the host's local/S3 storage backend with artifact read/write helpers. | Layout identical for all regulators; copy/delete tree operations work on local and S3 semantics; meta.json round-trips | 3 | Full-stack Engineer | Done | corpus_storage.py
REG-106 | E1 | Foundation & Configuration Framework | Sprint 1 | Foundation verification gate | A no-network CI gate proving configs parse, taxonomy is in sync, and all corpus tables register/create. | Single command exits non-zero on any foundation defect; run in CI on every commit | 2 | Backend Engineer | Done | scripts/regagg_verify_foundation.py — GREEN
REG-107 | E4 | Source Verification & Regulator Onboarding | Sprint 1 | Source verification harness | Automated verifier for every candidate source: reachability, content-type, parseability (incl. sitemap indexes), freshness; produces a per-regulator report. | Pass/warn/fail per source with reasons; sitemap-index recognized; report renders to markdown; harness is the only authority for verified:true | 5 | AI Engineer | Done | verify_sources.py; 29/30 regulators verified live
REG-108 | E4 | Source Verification & Regulator Onboarding | Sprint 1 | Fixture recorder & per-regulator parse tests | Record each regulator's real source payloads once and run every connector against its recording in CI. | Fixtures recorded for all reachable regulators; parametrized test per regulator passes offline; recordings size-capped | 3 | AI Engineer | Done | regagg_record_fixtures.py; tests/fixtures/ 29/30 (9.6MB)
REG-109 | E1 | Foundation & Configuration Framework | Sprint 1 | BA: source map validation & regulator list sign-off | Validate the proposed 30-regulator list and candidate sources against business priorities; obtain sign-off. | Signed-off regulator list; discrepancies (dead feeds, blocked sites) logged as onboarding risks | 2 | Business Analyst | Done | Source map verified; AMF block + 5 dead feeds logged and later remediated
PM-S1 | E1 | Foundation & Configuration Framework | Sprint 1 | PM: sprint ceremonies, RAID log, stakeholder reporting | Recurring per-sprint PM allocation (~25%): planning, standups, review/retro, risk and dependency management. | Ceremonies held; RAID log current; sprint report issued | 0 | Project Manager | Done | Recurring
REG-201 | E2 | Versioning & Governed Storage | Sprint 2 | Atomic versioning protocol (override→archive) | Six-step crash-safe protocol: stage new version, record intent, copy current to timestamped archive, promote staging, finalize document row. | New doc creates v1; changed content archives prior version and increments version; unchanged content is a no-op; document identity stable across revisions | 8 | Backend Engineer | Done | versioning.py; test_versioning.py
REG-202 | E2 | Versioning & Governed Storage | Sprint 2 | Crash-recovery reconciliation & invariant audit | Deterministic repair job that rolls half-applied updates forward, cleans orphan staging, and audits invariants (exactly one current per doc; archive append-only). | After any induced crash, reconcile restores a clean state with zero committed-data loss; violations are reported, never silently fixed twice | 5 | Backend Engineer | Done | versioning.reconcile(); /integrity endpoint OK on 5,969 docs
REG-203 | E2 | Versioning & Governed Storage | Sprint 2 | Chaos test suite for the versioning path | Automated tests that kill the pipeline after every protocol step and assert full recovery. | Crash injected at each of steps 1–5; invariants hold post-reconcile in all cases; reconcile idempotent | 3 | Backend Engineer | Done | test_versioning.py chaos parametrization (10 tests)
REG-204 | E3 | Collection Engine | Sprint 2 | Sitemap-diff connector | Detect new/changed URLs from sitemap.xml (incl. index recursion) plus listing pages, with lastmod fast-path skipping and include/exclude filters. | Sitemap+listing union deduplicated; known URLs with unchanged lastmod skipped; doc-type mapped from URL rules | 5 | AI Engineer | Done | connectors.SitemapDiffConnector; fixture + live tests
REG-205 | E3 | Collection Engine | Sprint 2 | RSS/Atom connector | Poll 1..n feeds per regulator with GUID→URL dedup, malformed-feed isolation, and backfill-cutoff filtering. | Duplicate GUIDs collapse; items older than cutoff ignored; one bad feed never aborts others | 3 | AI Engineer | Done | connectors.RssConnector; cutoff regression test
REG-206 | E3 | Collection Engine | Sprint 2 | API connector & Federal Register adapter | Provider-adapter API connector; Federal Register: agency filters, explicit field selection, pagination to cutoff, sanctioned full-text URL, abstract capture. | Paginates until backfill cutoff; emits reference numbers for dedup; requests raw_text_url+abstract explicitly (not in default fields) | 5 | AI Engineer | Done | connectors.ApiConnector; build_api_url; 500 docs/run
REG-207 | E3 | Collection Engine | Sprint 2 | Fetch & normalization layer | Polite fetcher (UA, per-domain rate limit) converting HTML→markdown (boilerplate stripped) and PDF→markdown, detecting PDFs by magic bytes, flagging scanned files. | HTML preserves headings/tables/links; .pdf URLs serving HTML are treated as HTML (magic-byte truth); scanned PDFs flagged ocr:true; content sha256 computed | 5 | Full-stack Engineer | Done | fetch.py; test_fetch.py incl. block-page regression
REG-208 | E2 | Versioning & Governed Storage | Sprint 2 | BA: provenance & audit acceptance walkthrough | Define and verify the governance chain a compliance reviewer needs: source URL, final URL, hash, timestamps, run attribution, raw original, version lineage. | Walkthrough from rendered doc back to original bytes and run manifest demonstrated; gaps (post-redirect URL) closed | 2 | Business Analyst | Done | Provenance tab; meta.json fields; 0 docs missing source_url
PM-S2 | E5 | Orchestration, Operations & Data Quality | Sprint 2 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager | Done | Recurring
REG-301 | E3 | Collection Engine | Sprint 3 | End-to-end ingestion pipeline | Wire detect→fetch→version→enrich→record per regulator: run manifests, seen-URL registry, per-URL error isolation, idempotent reruns. | One bad document never fails a run; rerun same day is a no-op for unchanged content; manifest lists every URL with outcome; run row persisted | 8 | Backend Engineer | Done | pipeline.run_regulator; OSFI e2e test incl. forced update→archive
REG-302 | E3 | Collection Engine | Sprint 3 | Policy-PDF harvesting | Extract same-domain PDF links from ingested HTML pages and ingest them as first-class policy documents (source_kind=policy_pdf), with per-page and per-run caps. | PDFs enter the same versioning path; source_kind recorded; caps prevent runaway; 3/page, 40/run defaults | 3 | AI Engineer | Done | 772 policy PDFs in corpus; harvest test
REG-303 | E3 | Collection Engine | Sprint 3 | Meta-source deduplication | When the meta-source (Federal Register) lists a document an agency feed already provided, keep the agency copy canonical and skip the duplicate by reference number. | Duplicate skipped and counted (deduped metric); no double-counting across fedreg/agency | 2 | AI Engineer | Done | meta_source flag; dedup test
REG-304 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | Fleet orchestrator | Fan out one isolated run per active regulator; support rerun of all/subset/one for a chosen date; expose reconcile as an operation. | One regulator's hard failure never blocks others; rerun records operator identity; reruns are idempotent | 5 | Backend Engineer | Done | orchestrator.py; isolation + rerun tests
REG-305 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | Run status semantics & live progress | Humane statuses (failed only when nothing landed or >20% errored) plus mid-run counter flushes so the UI can show live progress. | Partial-error runs show success + error count; counters update at least every 10 documents during a run | 3 | Backend Engineer | Done | events.finalize(); _flush_run; Today's-delta banner
REG-306 | E4 | Source Verification & Regulator Onboarding | Sprint 3 | Pilot regulators end-to-end (OSFI, FRB, FedReg) | Prove all three connector types live against the pilot trio, including a forced content change correctly archiving v1. | All pilots ingest live; update archives prior version; fixtures recorded | 3 | AI Engineer | Done | Live runs; OSFI 833→1,196 docs
REG-307 | E4 | Source Verification & Regulator Onboarding | Sprint 3 | Onboarding wave 1 — fifteen fast regulators | Verify sources and run first live ingestion for the non-giant regulators across all regions. | Each has ≥1 verified source and a passing live run; failures triaged with per-URL evidence | 5 | AI Engineer | Done | 18 regs at 100% of advertised coverage
REG-308 | E3 | Collection Engine | Sprint 3 | Crawl hardening | Protect the fleet from pathological sources: sitemap byte cap, sitemap-index child cap, giants-last ordering with per-giant caps, tuned timeouts. | A monster sitemap cannot hang a run (logged truncation); giants capped per run; hardening covered by tests | 3 | Full-stack Engineer | Done | 8MB/30-child caps after HKMA 3.8MB hang
REG-309 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | Bot-block guard & sanctioned fallbacks | Detect anti-scraping block pages and fall back to official API abstract, else an honest metadata stub — provenance labels content_source; never store block-page garbage; never evade. | Block page never stored as content; fallback chain full-text→abstract→stub; content_source recorded; zero recurring error storms | 2 | Full-stack Engineer | Done | FedReg: 64 abstracts + 436 stubs, 0 errors
REG-310 | E7 | Analyst & Operator Dashboard | Sprint 3 | BA: dashboard information architecture & status vocabulary | Define analyst/operator journeys, coverage semantics (fresh/stale/attention), and plain-language status labels for the UI. | IA for 5 pages agreed; status color/meaning table documented | 2 | Business Analyst | Done | Mockups reviewed; humane-status change driven by PO feedback
PM-S3 | E5 | Orchestration, Operations & Data Quality | Sprint 3 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager | Done | Recurring
REG-401 | E7 | Analyst & Operator Dashboard | Sprint 4 | Dashboard data API | Read endpoints backing every page: coverage tree with roll-ups, corpus browse with facets, changes feed, run overview with daily delta, version diff, inventory, jailed file explorer. | All endpoints stateless and paginated where relevant; institution filters applied in SQL before LIMIT; fs endpoints jailed to corpus root | 5 | Backend Engineer | Done | queries_ui.py + admin.py; endpoint tests incl. traversal + filter-order regressions
REG-402 | E7 | Analyst & Operator Dashboard | Sprint 4 | Coverage page | Region→institution expandable tree: web/PDF counts, new-in-window, last run, freshness pill, coverage-% vs source-advertised, per-row Run trigger. | Coverage % shown per institution; staleness flagged per config threshold; Run button triggers a real audited run | 5 | Full-stack Engineer | Done | /ui Coverage; auto-refresh during active runs
REG-403 | E7 | Analyst & Operator Dashboard | Sprint 4 | Corpus browser page | Dedicated deep-linkable page: continent/institution/file-type/doc-type/status/date/search filters with live facet counts, title+reference+excerpt rows, source links, Published+Added columns, pagination. | All filters server-side; facet counts reflect scope; row opens document drawer; 50/page with prev/next | 5 | Full-stack Engineer | Done | #corpus; excerpt layer exposed the FedReg block issue
REG-404 | E7 | Analyst & Operator Dashboard | Sprint 4 | Collection-runs page | Operations view: today's delta banner with pass-rate headline and failing-run digest, live active-run progress (5s polling), recent runs, daily delta history. | Pass-rate = fetched/(fetched+errors); live counters tick during runs; every run links to its manifest | 3 | Full-stack Engineer | Done | #run; verified against live crawls
REG-405 | E6 | Deterministic Enrichment & Knowledge Graph | Sprint 4 | Reference-number grammar & citation mining | Regex grammars for regulator identifiers (OSFI B/E-series, CAR/LAR chapters, SR letters, OCC bulletins, NI, APS, PS/CP/SS, RTS/ITS, BCBS…) extracting a document's own reference and its citations, with sentence-scoped supersede detection. | Own-reference extracted from titles; citations classified supersedes vs references without cross-sentence bleed; adding a grammar is a table entry | 5 | AI Engineer | Done | rules.py; pattern + sentence-scope tests
REG-406 | E6 | Deterministic Enrichment & Knowledge Graph | Sprint 4 | Cross-reference knowledge graph | Resolve citations against the corpus into typed edges with confidence; supersedes edges flip target status; unresolved citations persist and retry nightly. | Edges deduplicated; supersedes updates target to superseded; pending edges resolve when the target arrives | 3 | AI Engineer | Done | 176 edges + 756 pending on live corpus
REG-407 | E6 | Deterministic Enrichment & Knowledge Graph | Sprint 4 | Expected-inventory reconciliation (completeness proof) | Per-regulator expected inventories (seeded: OSFI CAR/LAR/B/E series) reconciled against the corpus by reference then title; per-series present/missing report and API. | Answers 'do we hold every chapter?' with named gaps; OSFI reconciles 30/30 after gap-fill | 3 | AI Engineer | Done | /inventory/osfi = 30/30; _inventories/osfi.yaml
REG-408 | E4 | Source Verification & Regulator Onboarding | Sprint 4 | Onboarding wave 2 — giants & source remediation | Onboard the large/broken regulators: capped depth-slicing for giants; fix dead feeds (FDIC), connector switches (HKMA + 5 RSS-dead regs → listing/sitemap), sitemap-index support (CSA). | 29/30 regulators verified and collecting; each fix re-verified by the harness; AMF escalated (not evaded) | 3 | AI Engineer | Done | eiopa/finra/iosco/mas/osc/hkma/fdic/csa all remediated
REG-409 | E4 | Source Verification & Regulator Onboarding | Sprint 4 | Targeted gap-fill runs | URL-regex-scoped ingest (e.g. /en/guidance) so specific sections can be completed without full-site crawls; used to complete OSFI's guideline chapters. | Scoped run ingests only matching URLs; OSFI guidance section filled (363 docs) driving inventory to complete | 2 | Backend Engineer | Done | --include flag; OSFI 12/30→30/30
REG-410 | E7 | Analyst & Operator Dashboard | Sprint 4 | BA: UAT round 1 (coverage/corpus/runs) | Structured UAT of the first three pages against analyst/operator journeys; log and triage defects. | UAT script executed; defects logged with severity; blocking defects fixed before sprint close | 2 | Business Analyst | Partial | Continuous PO review happened in-build (several defects caught: filters, statuses); formal scripted UAT pending
PM-S4 | E5 | Orchestration, Operations & Data Quality | Sprint 4 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager | Done | Recurring
REG-501 | E7 | Analyst & Operator Dashboard | Sprint 5 | Changes / impact feed | Analyst delta feed: NEW/REVISED/SUPERSEDED/DEADLINE cards grouped by day, filtered by region, institution, file type, change-type chips, and explicit date range — all server-side. | Filters share coverage-tree dimensions; counts remain pre-kind-filter for tile toggles; feed matches DB deltas exactly | 3 | Full-stack Engineer | Done | #chg; filter-before-LIMIT regression test
REG-502 | E7 | Analyst & Operator Dashboard | Sprint 5 | Version diff viewer | One-click unified diff between a document's current and previous archived version with added/removed counts, from the Changes feed and drawer. | Diff renders color-coded; single-version docs report 'no diff' cleanly | 2 | Full-stack Engineer | Done | /diff endpoint + viewer; real v1→v2 diffs verified
REG-503 | E7 | Analyst & Operator Dashboard | Sprint 5 | Rich document drawer | Document view with tabs: rendered markdown (self-contained md→html, no CDN), summary, provenance rail (all governance fields incl. final URL/fetch method/content source), raw text. | Headings/lists/tables/links render; provenance shows source URL clickable; raw preserved verbatim | 3 | Full-stack Engineer | Done | md2html engine; verified on live BoE paper
REG-504 | E7 | Analyst & Operator Dashboard | Sprint 5 | Corpus file Explorer | Nested file-tree page mirroring disk (regulator→current¦archive→doc_type→year→doc→artifacts) with lazy loading; text files open in drawer, originals download; API jailed to corpus root. | Path traversal rejected (400); item counts and sizes shown; md renders rich | 3 | Full-stack Engineer | Done | #exp; jail tests
REG-505 | E5 | Orchestration, Operations & Data Quality | Sprint 5 | Manual interjection & upload lane | Human override: add/update a document by URL fetch, pasted corrected markdown, or uploaded PDF/HTML — via UI modal, API, and CLI — through the identical versioning/provenance path, tagged manual and audited. | Update archives prior version; operator identity recorded; run row visible; future crawls recognize the URL (no duplicates); 50MB upload cap | 5 | Backend Engineer | Done | manual.py + modal + /documents(/upload) + CLI; v1→v2 test
REG-506 | E8 | MCP Tool Surface & Security | Sprint 5 | Content-plane MCP tools | reg_search (filter-then-rank), reg_read (summary¦full¦meta¦historical version), reg_tags, reg_whats_new, reg_graph — stateless, registered via config-driven dynamic discovery. | All five discoverable and callable over MCP; filters applied before ranking; graph traversal cycle-safe depth≤3 | 5 | AI Engineer | Done | reg_tools.py + generated configs; tool tests
REG-507 | E8 | MCP Tool Surface & Security | Sprint 5 | Index-plane MCP tools | reg_coverage, reg_browse (metadata-only), reg_changes, reg_diff, reg_inventory, reg_runs_status, reg_trigger_run (mutating, guarded) — the answers content-RAG cannot give. | All seven callable over MCP with the same filters as the UI; trigger refuses concurrent runs and records operator | 5 | AI Engineer | Done | Verified over the wire via agent key
REG-508 | E8 | MCP Tool Surface & Security | Sprint 5 | MCP security & key lifecycle | Authentication required for tools/call (discovery stays open); per-key tool allowlists enforced at the transport; scoped agent key issued, rotated, and stored DB-only (never committed). | No-key and dead-key calls rejected; out-of-scope tool denied; in-scope tool works — four-way matrix verified; rotation procedure documented | 5 | Backend Engineer | Done | api_routes enforcement; live verification matrix; key rotated pre-publication
REG-509 | E7 | Analyst & Operator Dashboard | Sprint 5 | BA: UAT round 2 (changes/diff/explorer/manual) | Structured UAT of the remaining pages and the manual lane. | UAT script executed; defects triaged; sign-off recorded | 2 | Business Analyst | Partial | In-build PO validation only; formal pass pending
PM-S5 | E5 | Orchestration, Operations & Data Quality | Sprint 5 | PM: sprint ceremonies & reporting | Recurring PM allocation. | As S1 | 0 | Project Manager | Done | Recurring
REG-601 | E9 | Agentic Integration | Sprint 6 | Markdown projection for the agent stack | Maintain the corpus in the agent tools' consumption layout — data/markdown/{web¦policy}/{regulator}/{doc_type}/{doc_id}.md with YAML frontmatter — via write-through on every ingest plus nightly resync self-heal. | Every current document has exactly one projection file; frontmatter carries citation context; resync idempotent; history stays in canonical store | 5 | Backend Engineer | Done | projection.py; 5,957 files (269MB); write-through test
REG-602 | E9 | Agentic Integration | Sprint 6 | Agent-platform MCP connectivity | Connect the existing agent stack to the MCP endpoint with the scoped key; verify end-to-end tool calls and denial of out-of-scope tools. | initialize/tools list/call verified from client side; connection details documented for the platform's custom-MCP dialog | 3 | AI Engineer | Done | Verified (usage counter); key details delivered
REG-603 | E9 | Agentic Integration | Sprint 6 | Chatbot enablement guide | Author the integration guide: connection block, agent prompt pattern (narrow→read cheap→relate→freshness), non-negotiable citation rule, worked examples, honest limitations, go-live eval checklist. | Guide sufficient for the chatbot team to integrate without our involvement | 2 | AI Engineer | Done | docs/regagg/CHATBOT_GUIDE.md
REG-604 | E9 | Agentic Integration | Sprint 6 | Agent skills authoring | Author skill definitions on the agent platform mapping to the tools: Daily Regulatory Briefing (reg_changes), Impact Analysis (reg_diff+reg_graph), Completeness Audit (reg_coverage+reg_inventory). | Three skills live on the platform; each produces correct, cited output on test prompts | 3 | AI Engineer | Not Started | Owner's agent platform; guide + tool surface ready
REG-605 | E9 | Agentic Integration | Sprint 6 | Agent citation & accuracy evaluation | Run the 20-question eval across ≥8 regulators: every claim cited (regulator+reference+date+URL), superseded docs flagged with successor, out-of-corpus questions declined. | Eval sheet completed with pass/fail per question; failures fed back into prompt/tool fixes | 3 | AI Engineer | Not Started | Checklist ready in CHATBOT_GUIDE; requires live agent stack
REG-606 | E5 | Orchestration, Operations & Data Quality | Sprint 6 | Daily delta poller & weekly deep run | Single scheduler entrypoint: fleet delta ingest (giants depth-sliced), pending-edge resolution, integrity reconcile, projection resync, one-line delta summary; weekly --deep raises caps. | One cron line each for daily/weekly; exit code signals invariant violations; every run visible in UI | 3 | Backend Engineer | Done | regagg_daily_poll.py; cron lines documented
REG-607 | E5 | Orchestration, Operations & Data Quality | Sprint 6 | Backup & restore | Nightly consistent SQLite snapshot + hardlink-incremental corpus backup with 7-day retention; restore verified. | Backup runs while server/crawls active; restore drill opens snapshot with full document count; retention enforced portably | 3 | Backend Engineer | Done | regagg_backup.sh; 2.0GB verified restore-check
REG-608 | E7 | Analyst & Operator Dashboard | Sprint 6 | UX polish round | Excerpt/description line + source links + Added date in corpus; PDF filename titles (incl. backfill); add-doc discoverability in top bar; rich-render defaults. | No raw URLs as titles; every row shows an honest excerpt where text exists; date column always populated | 3 | Full-stack Engineer | Done | 729 titles backfilled; excerpts live
REG-609 | E10 | Future Enhancements (Backlog) | Sprint 6 | Successor knowledge base | Author the handover KB: start-here mental model, architecture/flows/schema, UI+tools reference, testing/ops runbook, known issues + war stories + roadmap. | A new engineer/AI agent can operate and extend the system from the KB alone | 3 | Full-stack Engineer | Done | docs/regagg/kb/ (5 docs)
REG-610 | E9 | Agentic Integration | Sprint 6 | BA: final UAT & product-owner acceptance | End-to-end acceptance against the epic-level outcomes; PO sign-off for go-live. | Acceptance record signed; open items dispositioned to backlog | 2 | Business Analyst | Not Started | Pending PO session
PM-S6 | E5 | Orchestration, Operations & Data Quality | Sprint 6 | PM: go/no-go readiness review & handover | Deployment readiness review, handover of runbooks/KB, closure report. | Readiness review held; handover acknowledged | 0 | Project Manager | Not Started | Pending
REG-801 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | Infrastructure-as-code baseline for the aggregator | Codify the aggregator's AWS footprint (RDS access, S3 buckets/prefixes, ECR repo, ECS task definitions, EventBridge rules, IAM roles) as reviewable IaC in the platform's existing tooling, with per-environment parameters. | dev/staging/prod stacks deploy from code with no console steps; IAM follows least privilege; teardown/redeploy reproduces an identical environment; peer-reviewed and merged | 8 | Backend Engineer | Not Started | Requires platform/DevOps skills — see capacity assumption
REG-802 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | PostgreSQL migration & schema deployment | Deploy the reg_* schema into the existing production PostgreSQL (namespaced, no collisions with platform tables) and migrate the SQLite corpus index with full fidelity; establish forward migration tooling. | All 9 reg_* tables created via versioned migration; row counts and invariants match source exactly; one-current-per-doc enforced by partial unique index; rollback path documented; full test suite green against Postgres | 8 | Backend Engineer | Not Started | DDL shipped (003_regagg_schema.sql); reg_ prefix already prevents collisions
REG-803 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | S3 storage cutover for corpus and markdown projection | Switch the storage backend from local disk to S3 for the canonical corpus (raw/meta/versions/archive) and the agent-facing markdown projection, preserving the exact key layout the agent tools consume. | Existing ~6GB corpus migrated with checksum verification; ingestion writes to S3; projection paths unchanged for agent tools; archive immutability enforced via bucket policy/versioning; no local-disk dependency remains | 5 | Backend Engineer | Not Started | Storage abstraction already supports s3 backend
REG-804 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | Secrets and environment configuration management | Move API keys, database credentials and per-environment settings into the platform's secrets manager/parameter store; remove file-based keys; document rotation. | No credential exists in the repo or on disk; application resolves secrets at runtime per environment; key rotation performed without redeploy; rotation SOP documented | 3 | Backend Engineer | Not Started | Local build already rotated keys to DB-only
REG-805 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | Containerise collection workers | Package the collection pipeline as a container image (pinned dependencies, non-root, health check) published to the registry, runnable as a one-shot task. | Image builds reproducibly in CI; a task run performs a full regulator ingest against RDS+S3; image scanned for vulnerabilities with no criticals | 5 | Full-stack Engineer | Not Started
REG-806 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 8 | Cloud-scheduled daily and weekly ingestion | Replace host cron with cloud scheduling: daily delta run and weekly deep run as scheduled container tasks, with concurrency guard, timeout, retry and failure notification. | Daily/weekly schedules fire reliably; overlapping runs prevented; failures raise an alert; run history visible in the existing dashboard exactly as today | 5 | Backend Engineer | Not Started | Poller entrypoint + single-run guard already built
REG-807 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 8 | Cloud backup, retention and restore drill | Adopt platform-native durability: RDS automated backups with point-in-time recovery, S3 versioning plus lifecycle tiering for archive, and a documented restore procedure. | PITR verified by restoring to a scratch instance; S3 versioning protects against accidental deletion; lifecycle policy moves cold archive to cheaper tier; restore drill timed and documented against RPO/RTO targets | 5 | Backend Engineer | Not Started | Local backup script is the interim control
REG-808 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | BA: data classification, residency and retention sign-off | Confirm classification of the corpus (public regulatory content plus internal metadata), residency requirements and retention obligations for the cloud footprint. | Classification recorded; residency constraints reflected in region/bucket choices; retention schedule agreed with compliance | 2 | Business Analyst | Not Started
PM-S7 | E11 | Cloud Migration & Data Platform (AWS) | Sprint 7 | PM: sprint ceremonies, cloud dependency management | Recurring PM allocation plus coordination with the platform team. | Ceremonies held; cross-team dependencies tracked; sprint report issued | 0 | Project Manager | Not Started | Recurring
REG-901 | E13 | Production Integration, Security & Operations | Sprint 9 | Register reg_* tools on the production MCP server | Deploy the twelve reg_* tool definitions into the existing production MCP server so the production agent can call them, without forking platform code. | All twelve tools discoverable and callable in production; naming does not collide with existing platform tools; mutating tool (trigger run) gated by role; smoke test from the production agent passes | 5 | AI Engineer | Not Started | Tools are config-driven; index+content planes already built
REG-902 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 8 | Eliminate per-row object-store reads on the read path | Remove N+1 storage reads: persist document excerpts as a database column at ingest instead of reading each markdown file per listing row, and stop reading document bodies during search scoring. | Corpus listing issues a single database query with zero object-store calls; excerpt backfilled for existing corpus and maintained at ingest; p95 listing latency under target with cold cache | 5 | Backend Engineer | Not Started | Measured defect: 50-row page = 50 object reads
REG-903 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 8 | Delegate content search to the platform search layer | Point content retrieval at the platform's existing BM25/RAG index over the markdown projection, keeping the filter-then-rank contract; retire the interim in-process scorer. | reg_search filters in SQL then ranks via the platform index; results and citations equivalent or better than interim ranker; latency budget met on the full corpus | 5 | AI Engineer | Not Started | Owner's stack already provides BM25/RAG
REG-904 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 8 | Horizontally scalable stateless read tier | Run the dashboard/API tier as stateless replicas behind the platform load balancer with autoscaling, connection pooling to RDS, and graceful shutdown. | Service scales out and in under load with no session affinity; database connections bounded and pooled; rolling deploy causes no failed requests | 5 | Backend Engineer | Not Started | Thread-scoped sessions already fix pool leakage
REG-905 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 8 | Response caching for hot read endpoints | Cache coverage tree, facet counts and change-feed responses with short, explicit TTLs and invalidation on ingest completion. | Repeat dashboard loads served from cache; cache invalidated within one minute of a completed run; cache hit ratio and staleness observable | 3 | Full-stack Engineer | Not Started
REG-906 | E13 | Production Integration, Security & Operations | Sprint 9 | SSO authentication and role-based access control | Replace single-operator access with platform SSO and two roles: analyst (read) and operator (run, toggle, manual ingest); identity flows into the existing audit trail. | Unauthenticated access refused; analysts cannot trigger runs or manual ingests; every mutating action recorded with the authenticated identity; access matrix matches the signed-off definition | 8 | Backend Engineer | Not Started | Audit trail and operator attribution already implemented
REG-907 | E13 | Production Integration, Security & Operations | Sprint 9 | Per-tenant API keys, quotas and rate limiting | Issue scoped keys per team/agent with request quotas and rate limits so one consumer cannot degrade the service for 5,000 users. | Keys scoped to reg_* tools; quota and rate limit enforced with clear error responses; usage attributable per key; limits configurable without redeploy | 5 | Backend Engineer | Not Started | Allowlist enforcement already built
REG-908 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 9 | Queue-based parallel ingestion | Introduce a work queue between detection and fetch so multiple workers process documents concurrently, keeping the daily window comfortable as coverage depth grows, while preserving per-regulator politeness limits. | Full fleet run completes within the agreed window; per-domain rate limits still honoured; failures isolated per document; ordering-independent and idempotent | 8 | Backend Engineer | Not Started | Pipeline is already stateless and idempotent
REG-909 | E13 | Production Integration, Security & Operations | Sprint 8 | BA: role and access matrix definition | Define analyst/operator/administrator permissions across UI and tools and obtain security sign-off. | Matrix signed off; mapped to implemented roles; exceptions documented | 2 | Business Analyst | Not Started
PM-S8 | E13 | Production Integration, Security & Operations | Sprint 8 | PM: sprint ceremonies, integration coordination | Recurring PM allocation plus platform-team integration coordination. | Ceremonies held; integration risks tracked; sprint report issued | 0 | Project Manager | Not Started | Recurring
REG-1001 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 10 | Load and soak testing to 5,000 users | Define SLOs and prove them: model realistic analyst and agent traffic, run peak-load and multi-hour soak tests including a concurrent ingestion window. | Agreed SLOs documented; peak load sustained within latency budgets; soak shows no memory/connection leak; results reported with headroom analysis and breaking point identified | 8 | Backend Engineer | Not Started | Read load is user-driven; collection load is fixed
REG-1002 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 10 | Performance tuning from load-test findings | Address the bottlenecks the load test surfaces: query plans and indexes, pagination limits, payload sizes, and any remaining chatty calls. | Each identified bottleneck has a measured before/after; SLOs met with agreed headroom; changes covered by regression tests | 5 | Backend Engineer | Not Started
REG-1003 | E13 | Production Integration, Security & Operations | Sprint 10 | Observability: metrics, logs and dashboards | Emit structured logs and service metrics (ingestion volume and errors, corpus freshness, tool latency and error rate, queue depth) into the platform's monitoring stack with an operations dashboard. | Golden signals visible per service; ingestion and corpus health tracked over time; logs correlatable by run and request identifier | 5 | Full-stack Engineer | Not Started | Run manifests and counters already provide the data
REG-1004 | E13 | Production Integration, Security & Operations | Sprint 10 | Alerting and operational runbooks | Alert on the conditions that matter — failed or missed daily run, regulator staleness beyond threshold, integrity violation, elevated tool error rate — each with a runbook. | Every alert has an owner, severity and runbook; alerts tested by injecting each condition; no alert without a documented response | 3 | Backend Engineer | Not Started | Integrity check already exits non-zero on violations
REG-1005 | E13 | Production Integration, Security & Operations | Sprint 9 | CI/CD pipeline with automated quality gates | Automate build, test and deployment: full test suite and foundation gate on every change, image build and scan, staged deployment with rollback. | No manual deployment steps; pipeline blocks on failing tests or critical vulnerabilities; rollback exercised successfully at least once | 5 | Full-stack Engineer | Not Started | 92-test suite + foundation gate ready to wire
REG-1006 | E13 | Production Integration, Security & Operations | Sprint 10 | Security review and hardening | Complete pre-production security work: TLS everywhere, no default credentials, least-privilege IAM and bucket policies, dependency and image scanning, remediation of review findings. | Security review passed with no open high findings; default credentials eliminated; egress allow-list covers regulator domains; findings tracked to closure | 8 | Backend Engineer | Not Started | MANDATORY gate before exposure beyond localhost
REG-1007 | E12 | Scale & Performance (100 → 5,000 users) | Sprint 8 | Cost model and optimisation | Model steady-state cost (compute, RDS, S3 storage and requests, egress) at 5,000 users and apply the obvious optimisations; set budget alarms. | Cost per month projected with assumptions stated; S3 lifecycle tiering applied to archive; budget alarm configured; unit cost per user reported | 3 | Backend Engineer | Not Started
REG-1008 | E13 | Production Integration, Security & Operations | Sprint 10 | Production cutover and hypercare | Execute the cutover: final data sync, DNS/route switch, agent repointed to production tools, decommission of the interim environment, and a defined hypercare period. | Cutover run to a rehearsed plan with rollback available; no data loss verified by count and checksum; hypercare issues triaged daily; interim environment retired | 5 | Full-stack Engineer | Not Started
REG-1009 | E13 | Production Integration, Security & Operations | Sprint 10 | BA: production acceptance and go-live sign-off | Run acceptance against production with real users and obtain formal go-live approval. | Acceptance script executed in production; defects dispositioned; signed go-live approval recorded | 2 | Business Analyst | Not Started
PM-S9 | E13 | Production Integration, Security & Operations | Sprint 9 | PM: sprint ceremonies, security & integration coordination | Readiness review, cutover coordination, hypercare tracking and project closure. | Go/no-go held with documented decision; cutover coordinated; closure report issued | 0 | Project Manager | Not Started | Recurring
PM-S10 | E13 | Production Integration, Security & Operations | Sprint 10 | PM: hypercare tracking and project closure | Final sprint PM allocation: cutover coordination, hypercare triage, closure report and handover. | Hypercare issues triaged daily; closure report issued; handover acknowledged | 0 | Project Manager | Not Started | Recurring
REG-701 | E10 | Future Enhancements (Backlog) | Backlog | Federal Register full text via govinfo.gov bulk data | Replace abstract/stub fallback with sanctioned full text from GPO govinfo bulk repository (separate host built for programmatic bulk use). | Full text for new FR docs; existing stubs self-heal to full text as revisions; no ToS risk | 5 | AI Engineer | Not Started | Roadmap #1; adapter pattern ready
REG-702 | E10 | Future Enhancements (Backlog) | Backlog | Simple-mode overview landing page | First-time-user landing: one plain-English headline, ≤4 tiles, one regulator×(web/PDF/today delta/health-dot) table; ops detail moves behind drill-ins; analyst vs operator modes. | New user answers 'what do we have / what changed today / is it healthy' in <10s without training | 5 | Full-stack Engineer | Not Started | UX proposal documented
REG-703 | E10 | Future Enhancements (Backlog) | Backlog | Playwright fetch path for JS-heavy sites | Browser-rendered fetching for regulators whose listings require JavaScript (MAS, some NYDFS). | fetch:playwright configs ingest content where plain HTTP yields none | 5 | AI Engineer | Not Started | Config field already parses
REG-704 | E10 | Future Enhancements (Backlog) | Backlog | PostgreSQL migration | Flip db.type to Postgres using the shipped DDL; enable pg_trgm for title-similarity reference resolution. | All tests green on Postgres; no write-lock contention during concurrent crawl+agent load | 3 | Backend Engineer | Not Started | DDL ready
REG-705 | E10 | Future Enhancements (Backlog) | Backlog | Expected inventories for EBA / FCA / APRA | Extend completeness proofs beyond OSFI using each regulator's official register/index. | Per-series present/missing for 3 more regulators; gaps drive targeted gap-fills | 3 | AI Engineer | Not Started
REG-706 | E10 | Future Enhancements (Backlog) | Backlog | Weekly digest webhook | Teams/email digest generated from the changes feed (per-desk filters). | Scheduled digest delivered with citations; opt-in filters per audience | 3 | Backend Engineer | Not Started | Spec FR-9
REG-707 | E10 | Future Enhancements (Backlog) | Backlog | AMF Québec access via official whitelisting | Engage AMF for institutional IP/UA whitelisting (site bot-blocks all automation); fallback: licensed feed. | AMF collecting via sanctioned access; zero evasion techniques used | 2 | Business Analyst | Not Started | Escalated; contact pending
REG-708 | E10 | Future Enhancements (Backlog) | Backlog | Production hardening | Pre-exposure hardening: replace default admin credentials, TLS/reverse proxy, restricted bind, secrets management, key rotation SOP. | Security checklist passed before any non-localhost exposure | 5 | Backend Engineer | Not Started | MANDATORY before deployment beyond localhost
REG-709 | E10 | Future Enhancements (Backlog) | Backlog | OCR for scanned policy PDFs | Tesseract path for image-only PDFs (currently 6 docs, 97% extract fine without). | ocr:true docs gain searchable text; volume-triggered (revisit if scanned share grows) | 3 | AI Engineer | Not Started | Deprioritized by owner 2026-08-04
REG-710 | E10 | Future Enhancements (Backlog) | Backlog | LLM enrichment integration | Wire the owner's LLM gateway into the enrichment slot: real summaries (summary.md), taxonomy topic tags, doc-type reclassification, date/deadline extraction; golden-set eval gates. | Summaries replace excerpts; doc_type distribution reflects reality (not 90% announcement); deadline feed populated; eval ≥90% tagging accuracy | 8 | AI Engineer | Not Started | MockLLM slot + eval harness pattern in place

## Test Cases
TC ID | Story ID | Epic | Type | Test Case | Verifies | Status | Evidence
ATC-01 | REG-401/402 | E7 | Integration | test_coverage_matrix | Coverage matrix, drill-down, audited rerun/toggle, integrity | Pass | tests/regagg/test_admin.py::test_coverage_matrix
ATC-02 | REG-401/402 | E7 | Integration | test_regulator_detail_and_runs | Coverage matrix, drill-down, audited rerun/toggle, integrity | Pass | tests/regagg/test_admin.py::test_regulator_detail_and_runs
ATC-03 | REG-401/402 | E7 | Integration | test_rerun_is_audited | Coverage matrix, drill-down, audited rerun/toggle, integrity | Pass | tests/regagg/test_admin.py::test_rerun_is_audited
ATC-04 | REG-401/402 | E7 | Integration | test_toggle_flips_active_and_audits | Coverage matrix, drill-down, audited rerun/toggle, integrity | Pass | tests/regagg/test_admin.py::test_toggle_flips_active_and_audits
ATC-05 | REG-401/402 | E7 | Integration | test_integrity_ok | Coverage matrix, drill-down, audited rerun/toggle, integrity | Pass | tests/regagg/test_admin.py::test_integrity_ok
ATC-06 | REG-204/205/206/301/306 | E3 | Integration | test_sitemap_connector_detects_and_maps_doc_type | Connector detection per engine vs real configs; OSFI end-to-end incl. forced update→archive; rerun idempotency | Pass | tests/regagg/test_connectors_pipeline.py::test_sitemap_connector_detects_and_maps_doc_type
ATC-07 | REG-204/205/206/301/306 | E3 | Integration | test_sitemap_lastmod_fast_path_skips_unchanged | Connector detection per engine vs real configs; OSFI end-to-end incl. forced update→archive; rerun idempotency | Pass | tests/regagg/test_connectors_pipeline.py::test_sitemap_lastmod_fast_path_skips_unchanged
ATC-08 | REG-204/205/206/301/306 | E3 | Integration | test_rss_connector_dedups_and_parses | Connector detection per engine vs real configs; OSFI end-to-end incl. forced update→archive; rerun idempotency | Pass | tests/regagg/test_connectors_pipeline.py::test_rss_connector_dedups_and_parses
ATC-09 | REG-204/205/206/301/306 | E3 | Integration | test_api_connector_federal_register | Connector detection per engine vs real configs; OSFI end-to-end incl. forced update→archive; rerun idempotency | Pass | tests/regagg/test_connectors_pipeline.py::test_api_connector_federal_register
ATC-10 | REG-204/205/206/301/306 | E3 | Integration | test_osfi_end_to_end_create_then_forced_update_archives | Connector detection per engine vs real configs; OSFI end-to-end incl. forced update→archive; rerun idempotency | Pass | tests/regagg/test_connectors_pipeline.py::test_osfi_end_to_end_create_then_forced_update_archives
ATC-11 | REG-204/205/206/301/306 | E3 | Integration | test_rerun_same_day_is_idempotent | Connector detection per engine vs real configs; OSFI end-to-end incl. forced update→archive; rerun idempotency | Pass | tests/regagg/test_connectors_pipeline.py::test_rerun_same_day_is_idempotent
ATC-12 | REG-710 | E6 | Unit | test_enrich_classifies_tags_dates_and_supersedes | LLM-slot enrichment contract: taxonomy tags, dates never guessed, supersedes flip, enrichment_pending fallback | Pass | tests/regagg/test_enrichment.py::test_enrich_classifies_tags_dates_and_supersedes
ATC-13 | REG-710 | E6 | Unit | test_unresolved_reference_goes_to_pending_edges | LLM-slot enrichment contract: taxonomy tags, dates never guessed, supersedes flip, enrichment_pending fallback | Pass | tests/regagg/test_enrichment.py::test_unresolved_reference_goes_to_pending_edges
ATC-14 | REG-710 | E6 | Unit | test_invalid_llm_output_marks_enrichment_pending | LLM-slot enrichment contract: taxonomy tags, dates never guessed, supersedes flip, enrichment_pending fallback | Pass | tests/regagg/test_enrichment.py::test_invalid_llm_output_marks_enrichment_pending
ATC-15 | REG-207 | E3 | Unit+Regression | test_html_url_is_markdownified | HTML→md; PDF magic-byte routing (block-page regression); URL-title humanizer | Pass | tests/regagg/test_fetch.py::test_html_url_is_markdownified
ATC-16 | REG-207 | E3 | Unit+Regression | test_pdf_url_returning_html_is_treated_as_html | HTML→md; PDF magic-byte routing (block-page regression); URL-title humanizer | Pass | tests/regagg/test_fetch.py::test_pdf_url_returning_html_is_treated_as_html
ATC-17 | REG-207 | E3 | Unit+Regression | test_real_pdf_bytes_use_pdf_path | HTML→md; PDF magic-byte routing (block-page regression); URL-title humanizer | Pass | tests/regagg/test_fetch.py::test_real_pdf_bytes_use_pdf_path
ATC-18 | REG-207 | E3 | Unit+Regression | test_title_from_url_humanizes_pdf_names | HTML→md; PDF magic-byte routing (block-page regression); URL-title humanizer | Pass | tests/regagg/test_fetch.py::test_title_from_url_humanizes_pdf_names
ATC-19 | REG-506/507 | E8 | Integration | test_reg_search_ranks_and_filters | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_reg_search_ranks_and_filters
ATC-20 | REG-506/507 | E8 | Integration | test_reg_read_modes_and_version | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_reg_read_modes_and_version
ATC-21 | REG-506/507 | E8 | Integration | test_reg_tags_counts_and_category | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_reg_tags_counts_and_category
ATC-22 | REG-506/507 | E8 | Integration | test_reg_whats_new_window | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_reg_whats_new_window
ATC-23 | REG-506/507 | E8 | Integration | test_reg_graph_traverses_supersedes | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_reg_graph_traverses_supersedes
ATC-24 | REG-506/507 | E8 | Integration | test_generated_tool_configs_are_valid | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_generated_tool_configs_are_valid
ATC-25 | REG-506/507 | E8 | Integration | test_index_plane_tools | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_index_plane_tools
ATC-26 | REG-506/507 | E8 | Integration | test_trigger_tool_uses_runtime_trigger | All 12 MCP tools against seeded corpus; generated configs; trigger delegates to runtime | Pass | tests/regagg/test_mcp_tools.py::test_trigger_tool_uses_runtime_trigger
ATC-27 | REG-304 | E5 | Integration | test_daily_fanout_isolates_one_regulator_failure | Fleet fan-out failure isolation; audited subset rerun; reconcile | Pass | tests/regagg/test_orchestrator.py::test_daily_fanout_isolates_one_regulator_failure
ATC-28 | REG-304 | E5 | Integration | test_rerun_subset_is_idempotent | Fleet fan-out failure isolation; audited subset rerun; reconcile | Pass | tests/regagg/test_orchestrator.py::test_rerun_subset_is_idempotent
ATC-29 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[apra]
ATC-30 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[bis_bcbs]
ATC-31 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[boc]
ATC-32 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[boe_pra]
ATC-33 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[cftc]
ATC-34 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[csa]
ATC-35 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[eba]
ATC-36 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[ecb_ssm]
ATC-37 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[eiopa]
ATC-38 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[esma]
ATC-39 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[fca]
ATC-40 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[fdic]
ATC-41 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[fedreg]
ATC-42 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[fincen]
ATC-43 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[finra]
ATC-44 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[fintrac]
ATC-45 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[frb]
ATC-46 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[fsb]
ATC-47 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[hkma]
ATC-48 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[iais]
ATC-49 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[iosco]
ATC-50 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[jfsa]
ATC-51 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[mas]
ATC-52 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[nydfs]
ATC-53 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[occ]
ATC-54 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[osc]
ATC-55 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[osfi]
ATC-56 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[rbi]
ATC-57 | REG-108 | E4 | E2E-Fixture | test_connector_parses_recorded_payload | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_connector_parses_recorded_payload[sec]
ATC-58 | REG-108 | E4 | E2E-Fixture | test_fixture_coverage_report | Every regulator's connector parses its real recorded payload (29 regs) | Pass | tests/regagg/test_recorded_fixtures.py::test_fixture_coverage_report
ATC-59 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_extract_reference_number_patterns | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_extract_reference_number_patterns
ATC-60 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_extract_citations_supersede_vs_reference | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_extract_citations_supersede_vs_reference
ATC-61 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_apply_rules_creates_edges_and_pending | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_apply_rules_creates_edges_and_pending
ATC-62 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_pdf_harvest_and_source_kind | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_pdf_harvest_and_source_kind
ATC-63 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_meta_source_dedup_skips_agency_duplicates | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_meta_source_dedup_skips_agency_duplicates
ATC-64 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_rss_backfill_cutoff_skips_old_items | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_rss_backfill_cutoff_skips_old_items
ATC-65 | REG-405/406/302/303/601 | E6 | Unit+Integration | test_projection_write_through_and_layout | Reference grammars; sentence-scoped supersede; PDF harvest + source_kind; meta-source dedup; backfill cutoff; markdown projection | Pass | tests/regagg/test_rules_and_capture.py::test_projection_write_through_and_layout
ATC-66 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_tree_rollups_and_source_kind_split | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_tree_rollups_and_source_kind_split
ATC-67 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_browse_facets_and_filter | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_browse_facets_and_filter
ATC-68 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_changes_feed_marks_revision | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_changes_feed_marks_revision
ATC-69 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_version_diff | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_version_diff
ATC-70 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_runs_overview_shape | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_runs_overview_shape
ATC-71 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_changes_filters | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_changes_filters
ATC-72 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_changes_filter_finds_older_institution_rows | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_changes_filter_finds_older_institution_rows
ATC-73 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_doc_content_endpoint | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_doc_content_endpoint
ATC-74 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_manual_document_interjection | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_manual_document_interjection
ATC-75 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_fs_explorer_listing_and_jail | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_fs_explorer_listing_and_jail
ATC-76 | REG-401/403/501/502/504/505 | E7 | Integration+Regression | test_manual_upload_multipart | Tree/browse/changes/diff/runs/inventory endpoints; filter-before-LIMIT regression; manual add/update; multipart upload; fs jail | Pass | tests/regagg/test_ui_endpoints.py::test_manual_upload_multipart
ATC-77 | REG-107 | E4 | Unit | test_check_sitemap_pass | Reachability/content-type/parse/freshness checks; sitemap-index; report rendering | Pass | tests/regagg/test_verify_sources.py::test_check_sitemap_pass
ATC-78 | REG-107 | E4 | Unit | test_check_sitemap_stale_warns | Reachability/content-type/parse/freshness checks; sitemap-index; report rendering | Pass | tests/regagg/test_verify_sources.py::test_check_sitemap_stale_warns
ATC-79 | REG-107 | E4 | Unit | test_check_wrong_content_type_fails | Reachability/content-type/parse/freshness checks; sitemap-index; report rendering | Pass | tests/regagg/test_verify_sources.py::test_check_wrong_content_type_fails
ATC-80 | REG-107 | E4 | Unit | test_check_unreachable_and_404 | Reachability/content-type/parse/freshness checks; sitemap-index; report rendering | Pass | tests/regagg/test_verify_sources.py::test_check_unreachable_and_404
ATC-81 | REG-107 | E4 | Unit | test_check_feed_and_api_and_listing | Reachability/content-type/parse/freshness checks; sitemap-index; report rendering | Pass | tests/regagg/test_verify_sources.py::test_check_feed_and_api_and_listing
ATC-82 | REG-107 | E4 | Unit | test_verify_config_over_real_osfi_config | Reachability/content-type/parse/freshness checks; sitemap-index; report rendering | Pass | tests/regagg/test_verify_sources.py::test_verify_config_over_real_osfi_config
ATC-83 | REG-201/202/203 | E2 | Unit+Chaos | test_create_then_update_archives_previous | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_create_then_update_archives_previous
ATC-84 | REG-201/202/203 | E2 | Unit+Chaos | test_unchanged_content_is_noop | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_unchanged_content_is_noop
ATC-85 | REG-201/202/203 | E2 | Unit+Chaos | test_documents_row_tracks_current | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_documents_row_tracks_current
ATC-86 | REG-201/202/203 | E2 | Unit+Chaos | test_crash_then_reconcile_restores_invariant | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_crash_then_reconcile_restores_invariant[1]
ATC-87 | REG-201/202/203 | E2 | Unit+Chaos | test_crash_then_reconcile_restores_invariant | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_crash_then_reconcile_restores_invariant[2]
ATC-88 | REG-201/202/203 | E2 | Unit+Chaos | test_crash_then_reconcile_restores_invariant | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_crash_then_reconcile_restores_invariant[3]
ATC-89 | REG-201/202/203 | E2 | Unit+Chaos | test_crash_then_reconcile_restores_invariant | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_crash_then_reconcile_restores_invariant[4]
ATC-90 | REG-201/202/203 | E2 | Unit+Chaos | test_crash_then_reconcile_restores_invariant | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_crash_then_reconcile_restores_invariant[5]
ATC-91 | REG-201/202/203 | E2 | Unit+Chaos | test_crash_after_step1_keeps_old_current_and_cleans_staging | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_crash_after_step1_keeps_old_current_and_cleans_staging
ATC-92 | REG-201/202/203 | E2 | Unit+Chaos | test_reconcile_is_idempotent | Atomic override→archive protocol; crash injected at every step; reconcile restores invariants with zero loss | Pass | tests/regagg/test_versioning.py::test_reconcile_is_idempotent
MTC-01 | REG-508 | E8 | Security-Manual | MCP auth matrix over the wire | No key→401; disabled key→401; valid key + reg tool→200; valid key + out-of-scope tool→denied (-32001) | Pass | curl matrix 2026-08-04
MTC-02 | REG-508 | E8 | Security-Manual | API key rotation | Old key dead everywhere; new DB-only key works; committed copy scrubbed before repo publication | Pass | rotation 2026-08-03
MTC-03 | REG-401 | E7 | Security-Manual | Connection-pool endurance | 30 rapid API calls with 5s-polling load; no pool exhaustion | Pass | hammer test post thread-scoped sessions
MTC-04 | REG-407 | E6 | System | OSFI completeness reconciliation | Inventory reports 30/30 (CAR 9/9, LAR 5/5, B 8/8, E 8/8) after guidance gap-fill | Pass | /inventory/osfi
MTC-05 | REG-307/408 | E4 | System | Live fleet collection | 29/30 regulators verified and collecting; ~5,970 docs; per-regulator coverage % reported | Pass | live crawls 2026-08-02..04
MTC-06 | REG-309 | E5 | System | FedReg fallback chain | All ~500 FR docs carry abstract or labeled stub; content_source in provenance; zero error storm | Pass | fedreg re-ingests
MTC-07 | REG-607 | E5 | System | Backup + restore check | Consistent snapshot while live; restored DB opens with full doc count; retention pruning | Pass | 2.0GB backup restore-check
MTC-08 | REG-201 | E2 | System | Live update→archive | Real revised pages produce v2 with prior version archived and diff viewable | Pass | 6 live revisions (frb/boe_pra/fca)
MTC-09 | REG-402..404 | E7 | UAT-Manual | Dashboard smoke on live data | All 5 pages render live corpus; drill-downs, drawer, diff, rerun guard behave | Pass | browser walkthroughs
MTC-10 | REG-505 | E5 | UAT-Manual | Manual lane end-to-end | URL-fetch, pasted-markdown, and PDF-upload paths create/version docs with manual tag + audit | Pass | API+UI verification
MTC-11 | REG-601 | E9 | System | Projection integrity | 5,957 projection files match current corpus; frontmatter valid; resync idempotent | Pass | resync report
MTC-12 | REG-304 | E5 | System | Concurrent-run guard | Second fleet trigger refused while a run is active | Pass | live rerun attempt
MTC-13 | REG-106 | E1 | Gate | Foundation gate | 30/30 configs parse; taxonomy sync; 9 tables register/create | Pass | regagg_verify_foundation.py
MTC-14 | REG-605 | E9 | UAT-Manual | Agent citation eval (20 questions) | Every answer cites regulator+reference+date+URL; declines out-of-corpus | Not Run | awaiting owner agent stack

## Summary
Execution Summary
Total stories | 102
Done | 56
Partial | 2
Not started | 44
Story points — Done | 190
Story points — total (incl. backlog) | 375
Automated test cases (Pass) | 100
Manual/system verifications (Pass) | 13
Pending verifications | 1